## 2023 PM & TM Activities
PM & TM Activities - 2023
[10 empty] | Main Activity | [6 empty] | Sessions / Workshops | [12 empty] | Communication
[10 empty] | 2022-11-01 |  |  |  | 2022-12-01 |  |  |  | 2023-01-01 |  |  |  | 2023-02-01 |  |  |  | 2023-03-01 |  |  |  | 2023-04-01 |  |  |  | 2023-05-01 |  |  |  | 2023-06-01 |  |  |  | 2023-07-01 |  |  |  | 2023-08-01 |  |  |  | 2023-09-01 |  |  |  | 2023-10-01 |  |  |  | 2023-11-01 |  |  |  | 2023-12-01
[10 empty] | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07
Objectives | Activity | Responsibility |  |  |  | KPIs | Timelines
|  | TM | HRBP | Line Manager | Employee |  | Start | End | Days
2022 Year End Evaluation | Corporate Communication & Release the form on the system | 2 |  |  |  |  | 2022-12-05 | 2022-12-05 | 1
| Enablement sessions for HRPBs | 2 |  |  |  |  | 2022-12-05 | 2022-12-20 | 15
| Enablement sessions for Employees | 2 | 2 |  |  |  | 2022-12-05 | 2022-12-20 | 15
| Enablement sessions for Line managers | 2 | 2 |  |  |  | 2023-01-02 | 2023-01-20 | 18
| Complete the self-evaluation on the system |  |  |  | 2 |  | 2022-12-05 | 2023-01-31 | 57
| complete the performance discussion with the employees |  |  | 2 | 2 |  | 2022-12-01 | 2023-01-31 | 61
| Complete the line manager rating on the system |  |  | 2 |  |  | 2022-12-01 | 2023-01-31 | 61
2022 Calibration | Enablement session HRBPs, LMs | 2 | 2 |  |  | 100% completion | 2023-01-15 | 2023-01-31 | 16
| Calibration meetings with the Line manager |  | 2 | 2 |  |  | 2023-01-15 | 2023-01-31 | 16
| Finalize Calibration meetings with the HODs |  | 2 |  |  |  | 2023-02-01 | 2023-02-15 | 14
| 2022 Calibration Rating Communication | 2 |  |  |  |  | 2023-03-01 | 2023-03-01 | 1
| Employees Appeal - Within 5 days of the rating communication |  | 2 |  | 2 |  | 2023-03-02 | 2023-03-23 | 21
2023 Goal Setting | Release the Form on the system | 2 |  |  |  | 95% completion | 2023-01-02 | 2023-01-02 | 0
| Corporate comms communication | 2 |  |  |  |  | 2023-01-23 | 2023-01-30 | 7
| Enablement sessions & materials for Line managers | 2 | 2 |  |  |  | 2023-01-26 | 2023-02-10 | 15
| Enablement sessions for employees | 2 | 2 | 2 |  |  | 2023-01-26 | 2023-02-15 | 20
| Conduct Goal-setting workshops | 2 | 2 | 2 |  |  | 2023-01-02 | 2023-02-28 | 57
| Completion of the goal settings on the system |  |  |  | 2 |  | 2023-01-02 | 2023-03-15 | 72
| Goal Audit for 5 % of the Population | 2 |  |  |  |  | 2023-05-01 | 2023-06-01 | 31
Critical Role Identification | Review the critical role & share updated with TM |  | 2 | 2 |  | * Critical Roles to Future Business Needs | 2023-02-15 | 2023-02-28 | 13
Talent Identification | Talent Planning Kick off | 2 | 2 | 2 |  | * Building successor profiles * Assess development needs * Enabling employees Career path * Employees segment and satisfaction | 2023-06-01 | 2023-07-01 | 30
| Configuring the Talent Module on Igrow | 2 |  |  |  |  | 2023-02-01 | 2023-05-01 | 89
| Update data on the tool | 2 | 2 |  |  |  | 2023-06-01 | 2023-07-01 | 30
| Enablemnt session for HRBPs & Line managers | 2 | 2 | 2 |  |  | 2023-06-01 | 2023-07-01 | 30
| Update employees talent cards |  | 2 | 2 | 2 |  | 2023-03-01 | 2023-03-31 | 30
| Talent Planning Meetings |  | 2 | 2 |  |  | 2023-07-01 | 2023-09-01 | 62
| Quarterly review and status update |  | 2 | 2 | 2 |  | Aug/ Nov 2023
Continuous Performance Management | Release Communcation for CPM | 2 |  | 2 | 2 | Ensure 80 % Utilization of CPM | June - Nov
| Leverage the Intranet & Microtips | 2 | 2
| Develiver Enabelment session on Continous Conversation & how to use CPM | 2 | 2
| CPM Simulation Utilization | 2 | 2
| Reporting to TM Leads | 2 | 2
360 Leadership Assessment | Roll out the 360 Leadership assessment | 2 | 2 |  |  | 100% of band G/H people managers enrolled in Emerging Leader program with 360 completed
Career Growth & IDP | e-mail communication to roll out the career growth & IDP | 2 |  |  |  |  | 2023-05-01 | 2023-05-15 | 14
| Weekly Microtips on teams | 2 |  |  |  |  | 2023-05-01 | 2023-06-15 | 45
| Posters & Banners for Activation | 2 | 2 |  |  | 90% of our Employees with IDP | 2023-05-01 | 2023-05-05 | 4
| Training session to all HRBP & Divisional TM Leads on career growth & IDP and share the activation plan | 2 | 2 |  |  |  | 2023-05-01 | 2023-05-15 | 14
| Deliver Workshops F2F & Virtual to all employees on career growth & IDP | 2 | 2 | 2 | 2 |  | May-July
| Deliver session on Career Success & IDP on Drive In | 2 | 2 |  |  |  | 2023-05-01 | 2023-06-15
| Self paced e-learning module to help employees develop their IDP. | 2
| Dedicate 1 hour to respond to any challenge that the employee faces in IDP. | 2 | 2 |  |  |  | June & Oct 2023
| Invite different leaders to a Panel discussion to share their career success stories, challenges they faced and how they leveraged the leadership competencies. | 2 | 2 |  |  |  | 2023-01-01 | 2023-01-31 | 30
Enable | Roll Out the Process & Policy | 2 |  |  |  | 100 % of Employees who were rated NM (1) are on Enable | 2023-03-01 | 2023-03-15 | 14
| Conduct Enablement Sessions for HRBPs | 2 |  |  |  |  | 2023-04-01 | 2023-04-20 | 19
| Conduct Enablement Sessions for LMs | 2 |  |  |  |  | 2023-04-15 | 2023-04-30 | 15
| Configure the Enable module on SF | 2 |  |  |  |  | 2023-01-01 | 2023-06-01 | 151
| Conduct Enablement Session for System naviagtions for HRBPS & LMs | 2 |  |  |  |  | 2023-06-15 | 2023-06-30 | 15
| Conduct Refresher session for LMs | 2 |  |  |  |  | 2023-06-15 | 2023-06-30 | 15
| Reporting & tracking | 2 | [5 empty] | All year Round

## 2023 PM & TM Calendar
Dec 2022 /
Jan 2023
Feb
Mar
Apr
May
Jun
July
Aug
Sept
Oct
Nov
Dec
Talent
Calibration
Sessions
Workforce Planning
Career Growth & IDP Activation
360 Leadership assessment
2023 Annual Perormance Review
CPM Activation
Talent Activity Planner
2022 Annual
Performance
Review
2023 PM & TM Communication plan
Rating Communication
Appeal
Goal Setting
IDP
Discussion
Talent Identification & Planning
Enable
Goal Audit
Critical Role Identification