## Slide 1: Goal Setting Activation Plan
Activity | Description | Audience | Date
Education session | Train the Trainer for HRBPs and TM Leads to drive the Goal setting workshop | HRBP/ Division TM Leads | 16-01-2023
HR Comms | E-mail notifying people managers about the release of Goal Setting form 2023 & The need to align, cascade and set priorities for the team. | People Managers | 23-01-2023
HR Comms | E-mail notifying employees that the Goal setting Form 2023 is released & what is expected from them. | Employees | 24-01-2023
Goal Setting Simulation | E-learning module release (in cases where face to face workshop is not possible) - supporting people managers in the full Goal Setting Process. | People manager | 24-01-2023
Goal Setting workshop | HRBP to co-facilitate Goal Setting workshops with divisional/functional leaders | People Manager with their teams | From 17-01-2023 To 15-03- 2023
Banner | Highlighting the deadline & connecting to the Goal Setting Tool kit on iGROW | All | From 30-01-2023 To 15-03- 2023
iGrow Toolkit | Complete toolkit for Goal Setting with different tips for both people manager and employees on the full Goal Setting process. | All | 06- 02-2023
SMS & Info Alert on TEAMs | Reminder for all employees to log their goals before deadline. | All | 08/14-03-2023