## 2023 TM Planner
2023 Talent Management & Events Calendar
[10 empty] | Main Activity | [6 empty] | Sessions / Workshops | [12 empty] | Communication
[10 empty] | 2022-11-01 |  |  |  | 2022-12-01 |  |  |  | 2023-01-01 |  |  |  | 2023-02-01 |  |  |  | 2023-03-01 |  |  |  | 2023-04-01 |  |  |  | 2023-05-01 |  |  |  | 2023-06-01 |  |  |  | 2023-07-01 |  |  |  | 2023-08-01 |  |  |  | 2023-09-01 |  |  |  | 2023-10-01 |  |  |  | 2023-11-01 |  |  |  | 2023-12-01
[10 empty] | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07
Objectives | Activity | Responsibility |  |  |  | Expected Outcome | Timelines
|  | TM | HRBP | Line Manager | Employee |  | Start | End | Days
2022 Year End Evaluation | Confirmation on the 100% employees goal completion on the system |  | 2 |  |  | 100% completion | 2022-11-15 | 2022-11-30 | 15
| Corporate Communication & Release the form on the system | 2 |  |  |  |  | 2022-12-05 | 2022-12-05 | 1
| Enablement sessions for HRPBs | 2 |  |  |  |  | 2022-12-05 | 2022-12-20 | 15
| Enablement sessions for Employees | 2 | 2 |  |  |  | 2022-12-05 | 2022-12-20 | 15
| Enablement sessions for Line managers | 2 | 2 |  |  |  | 2023-01-02 | 2023-01-20 | 18
| Complete the self-evaluation on the system |  |  |  | 2 |  | 2022-12-05 | 2023-01-31 | 57
| complete the performance discussion with the employees |  |  | 2 | 2 |  | 2022-12-01 | 2023-01-31 | 61
| Complete the line manager rating on the system |  |  | 2 |  |  | 2022-12-01 | 2023-01-31 | 61
2022 Calibration | Enablement session HRBPs, LMs | 2 | 2 |  |  | PRD Rating completion | 2023-01-15 | 2023-01-31 | 16
| Discussion meetings with the Line manager |  | 2 | 2 |  |  | 2023-01-15 | 2023-01-31 | 16
| Finalize Calibration meetings with the HODs |  | 2 |  |  |  | 2023-02-01 | 2023-02-15 | 14
| LMs communicate the rating to employees |  | 2 | 2 |  |  | 2023-02-15 | 2023-02-28 | 13
| 2022 Calibration Rating Communication | 2 |  |  |  |  | 2023-03-01 | 2023-03-01 | 1
| Employees Appeal - Within 15 days of the rating communication |  | 2 |  | 2 |  | 2023-03-02 | 2023-03-23 | 21
2023 Individual Goal Setting | Release the Form on the system | 2 |  |  |  | 100% goal setting completion | 2023-01-02 | 2023-01-02 | 0
| Corporate comms communication | 2 |  |  |  |  | 2023-01-23 | 2023-01-30 | 7
| Enablement sessions & materials for Line managers | 2 | 2 |  |  |  | 2023-01-26 | 2023-02-10 | 15
| Enablement sessions for employees | 2 | 2 | 2 |  |  | 2023-01-26 | 2023-02-15 | 20
| Line manager & employee objective-setting meetings |  |  | 2 | 2 |  | 2023-01-02 | 2023-02-28 | 57
| Completion of the goal settings on the system |  |  |  | 2 |  | 2023-01-02 | 2023-03-15 | 72
Critical Role Identification | Review the critical role & highlight the ones included in the talent value exercise |  | 2 | 2 |  | *Proactive Identification Based on Company Needs * Forecast and Plan for Change * Critical Roles to Future Business Needs | 2023-02-15 | 2023-02-28 | 13
Talent Identification | Talent identification initial meeting | 2 | 2 | 2 |  | * Building successor profiles * Assess development needs * Enabling employees Career path * Employees segment and satisfaction | 2023-02-01 | 2023-02-15 | 14
| Potential assessment by line manager |  |  | 2 | 2 |  | 2023-02-01 | 2023-02-15 | 14
| Collect employee data/ Submit Top talents list after consolidation |  | 2 | 2 |  |  | 2023-02-15 | 2023-02-28 | 13
| Top Talent Calibration (9 box performance) |  | 2 | 2 |  |  | 2023-02-15 | 2023-02-28 | 13
| Run external assessment for the top 3 talents | 2 | 2 | 2 | 2 |  | 2023-03-01 | 2023-03-31 | 30
| Talent Card - Band H+ |  | 2 | 2 |  |  | 2023-03-01 | 2023-03-31 | 30
| Download and map the data from the talent cards |  | 2 |  |  |  | 2023-04-01 | 2023-04-07 | 6
| Anticipate vacancies for the next 12 month |  | 2 | 2 |  |  | 2023-04-01 | 2023-04-08 | 7
| Talent Discussion ( Identifying prioritized successors, Hi- Pos and candidate slate for new vacancies) |  | 2 | 2 |  |  | 2023-04-08 | 2023-04-30 | 22
| Action plan with all agreed points |  | 2 |  |  |  | 2023-04-08 | 2023-04-30 | 22
| Top talent IDPs setting with employees |  |  | 2 | 2 |  | 2023-05-01 | 2023-05-31 | 30
| IDP Sign off meeting |  |  | 2 | 2 |  | 2023-05-01 | 2023-05-31 | 30
| Quarterly review and status update |  | 2 | 2 | 2 |  | Aug/ Nov 2023
Continuous Performance Management | Quarterly meeting to follow up on action plan & discuss any support needed |  | 2 | 2 | 2 | Ensure action plan is executed on time. | June/ Sep/Dec/ March
| Enablement sessions, Develop and update Toolkits | 2 |  |  |  |  | June/ Sep/Dec/ March
360 Leadership Assessment | Roll out the 360 Leadership assessment | 2 | 2 |  |  | All the year around
Engagement & Wellbeing | Monthly engagement calendar/ Design of the activities & initiative recommendation | 2 |  |  |  | All the year around | 2023-01-01 | 2023-12-30 | 363
| Monthly Wellbeing calendar / Organisation of monthly webinars & monthly wellbeing newsletter | 2 |  |  |  | All the year around | 2023-01-01 | 2023-12-31 | 364
| Growing together Survey Results | 2 |  |  |  | HRD to share Divisional results | 2023-01-01 | 2023-01-31 | 30
| Growing together Survey Action Planning & workshops |  | 2 |  |  |  | 2023-01-01 | 2023-03-30 | 88
| Growing together Survey Action Planning Follow Up |  | 2 |  |  |  | May & Sep 2023
| Engagement Pulse Surveys Define the areas of focus, set up, communicate and run the surveys & reports |  | 2 |  |  |  | June & Oct 2023
| Launch of UAE EAP | 2 |  |  |  |  | 2023-01-01 | 2023-01-31 | 30
Experience & Culture | Unified monthly onboarding event | 2 | 2 |  |  | All the year around | 2023-01-01 | 2023-12-31 | 364
| Relaunch of Values & development of all materials | 2 |  |  |  |  | 2023-01-01 | 2023-01-31 | 30
| Bringing Values to life | 2 |  |  |  |  | 2023-02-01 | 2023-05-01 | 89
Learning & Leadership Development | Level 1 Leadership Journey : Design of Modules & TTT together with running of a central cohort | 2 |  |  |  | L&D to contribute the ideas HRBPs to enable the implementation | 2023-01-01 | 2023-10-01 | 273
| Level 2 Leadership Journey: Design of Module content & structure | 2 |  |  |  |  | 2023-01-01 | 2023-03-01 | 59
| Level 2 Leadership Journey : Co-ordinate delivery of central cohort | 2 |  |  |  |  | 2023-05-01 | 2023-11-30 | 213
| Drive-in, MINT and LEAD : Define the monthly calendar of learning events | 2 |  |  |  |  | All the year
| Design and drive the events of the idigital Leadership series targeting Band J & above | 2
| Design learning paths and session content for idigital Data Analytics Academy | 2